## Sheet1
Week | Task Name | Description | Hours | Status
Setup and framing the project
10/08-10/14 | Functional Spec | Function spec, review/revise existing plans | 2
10/08-10/14 | Mockups | Wireframes/mockups, review and revise existing plans | 2
10/08-10/14 | Setup | Git, project setup, kivy tutorials (Uis, unit tests, working with camera/video) | 3
10/08-10/14 | Create Base GUI Template | Create a base GUI which other GUIs use, unfamiliar territory -- mainly a CLI dev | 3
10/08-10/14 | Weekly Status Check 1 | Send in weekly status check | 0.25
10.25
Stubs and GUI frames
10/15-10/21 | Initial GUIs + Unit Tests | Home page, story book, story library | 6
10/15-10/21 | Library and Story template config | Global config will store globally relevant details such as color settings, library names; create config file which will be used as a story template ; each story will have a separate config file | 3
10/15-10/21 | Class stubs + unit tests | Create unit tests and stubs for: Page, CustomData, Media, StoryTemplate, Library, Creator | 4
10/15-10/21 | Weekly Status Check 2 | Send in weekly status check | 0.25
13.25
Story functionality and presentation
10/22-10/28 | Basic content creation for initial testing | Stories, images, videos, custom data | 3
10/22-10/28 | Story Functionality | Title page displays correctly; Load story from config; Next page, prev page, home buttons work; Static text, video and images display | 5
10/22-10/28 | Intermediate Milestone 1 | Create trailer or presentation | 2
10/22-10/28 | Weekly Status Check 3 | Send in weekly status check | 0.25
10.25
Creator Dive
10/29-11/04 | Library functionality | Load stories from library config and display in GUI | 2
10/29-11/04 | Create Creator GUIs + unit tests | Creator Home; Title page/story settings editor; Custom data editor; Story page editor | 6
10/29-11/04 | Polishing and revisions | Space for polishing | 3
10/29-11/04 | Weekly Status Check 4 | Send in weekly status check | 0.25
11.25
Creator Part II
11/05-11/11 | Functionaity title page editor | Title and other settings can be set; Number of pages can be updated; Settings can be saved | 4
11/05-11/11 | Page editor | Text can be added; Media can be added from computer | 6
11/05-11/11 | Intermediate Milestone 2 | Functional Demo for beta test | 2
11/05-11/11 | Weekly Status Check 5 | Send in weekly status check | 0.25
12.25
Custom Data
11/12-11/18 | Custom data editor | New custom data can be created; custom data can be edited; custom data can be saved | 4
11/12-11/18 | Custom data display | Custom data can be displayed in text and title | 4
11/12-11/18 | Polishing and revisions | Space for polishing | 3
11/12-11/18 | Weekly Status Check 6 | Send in weekly status check | 0.25
11.25
Content creation
11/19-11/25 | Default story content creation | Create stories with default images, text for use in initial library | 8
11/19-11/25 | GUI refinement | Adjust colors, styles, add customization | 2
11/19-11/25 | Final Evaluation | Evaluate checklist from proposal | 1
11/19-11/25 | Weekly Status Check 7 | Send in weekly status check | 0.25
11.25
Advanced functionality
11/26-12/02 | Page editor advanced | Media can be added from url; Media can be added from direct capture | 6
11/26-12/02 | Video time frames | Video can be set to start and stop playing at given points in the video | 4
11/26-12/02 | Advanced evaluation | Evaluate additional features | 1
11/26-12/02 | Weekly Status Check 8 | Send in weekly status check | 0.25
11.25
Final preparations
12/03-12/09 | Final project | Prepare submission of final project, last testing, README | 1.5
12/03-12/09 | Final paper | Prepare paper on project | 5
12/03-12/09 | Final presentation | Prepare presentation on project | 3
|  | Hours | 9.5
|  | Total Hours | 100.5